## Sprint
Functional Testing Case Study - 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://www.zeptonow.com/
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the Dependacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Zepto is a fast-growing online grocery delivery platform that offers a wide range of products including fresh fruits and vegetables, dairy, snacks, beverages, household essentials, and personal care items. Known for its ultra-fast delivery—often within minutes—Zepto aims to provide a seamless and efficient shopping experience for daily needs. FUNCTIONALITY IN THE SCOPE (What Functioanlities to TEST): 1) Search Product - Open the Zepto website and locate the search bar. - Search for categories like Fruits, Vegetables, Dairy, Snacks, etc. - Example: Search for “Bananas” under Fruits or “Amul Milk” under Dairy. - Validate that relevant products are displayed with correct names, images, and prices. 2) Super Saver & Offers - Apply the Super Saver filter to view discounted products. - Validate that products with active offers are correctly tagged. - Check if promo codes or vouchers can be applied during checkout. - Example: Look for “Buy 1 Get 1” or “Flat ₹20 off” labels. 3) Add to Cart - Select products based on quantity, price, and preference. - Add selected items to the cart. - Verify: - Cart count increases correctly. - Product name, quantity, and price are accurate. - Discounts (if any) are applied and visible. 4) Checkout & Delivery - Click on the cart and proceed to checkout. - Steps to test: - Confirm or add a delivery address. - Review cart summary and product details.
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report Keep all the Deliverables on Git
Sprint Day 5 | Sprint Evaluation

## User Stories
Issue Type | Summary
Epic 1 | User Login
Story 1 | As a customer, I should be able to log in to the Zepto website using a valid mobile number and OTP, so I can securely access my account.
Story 2 | As a customer, I want to receive a clear error message when I enter an invalid mobile number or incorrect OTP, so I understand what went wrong and can try again.
Epic 2 | Product Discovery & Search
Story 1 | As a customer, I want auto-suggestions in the search bar so I can quickly find relevant grocery items.
Story 2 | As a customer, I want to navigate product categories so I can browse items by type (e.g., Fruits, Dairy, Snacks).
Epic 3 | Savings & Offers
Story 1 | As a customer, I want to view products with Super Saver tags so I can identify discounted items easily.
Story 2 | As a customer, I want to apply promo codes during checkout to reduce my total bill.
Epic 4 | Cart Functionality
Story 1 | As a customer, I want an "Add to Cart" option so I can prepare my order for checkout.
Story 2 | As a customer, I want to remove items from my cart before placing the order.
Epic 5 | Delivery Address Management
Story 1 | As a customer, I want to add a delivery address where my groceries should be delivered.
Story 2 | As a customer, I want to edit or delete saved addresses for convenience.

## Test Case Template
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Automation Results
TC_LOGIN_001 | Verify User Login with Correct OTP | User is registered and has access to a valid mobile number | Validate login using a valid mobile number and correct OTP | 1. Open browser 2. Navigate to https://www.zeptonow.com 3. Click “Login” 4. Enter registered mobile number 5. Click “Send OTP” 6. Enter the correct OTP received on the mobile 7. Click “Verify” | Mobile Number: 9876543210 OTP: 123456 (example OTP) | User is successfully logged in and redirected to the homepage
TC_SEARCH_002 | Verify Product Search and Super Saver Filter | User is logged in | Validate search and filter functionality | Login to Zepto Enter “Milk” in search bar Apply “Super Saver” filter | Search term: Milk | Filtered products with discounts are displayed
TC_CART_003 | Verify Add to Cart Functionality | User is logged in and has searched for a product | Validate product addition to cart | Search for “Amul Milk” Click “Add to Cart” Open cart Verify product name, quantity, and price | Product: Amul Milk 1L | Product appears in cart with correct details
TC_CART_004 | Verify Cart Persistence After Logout/Login | Product added to cart | Validate cart retains items after logout/login | Add product to cart Logout from Zepto Login again Open cart | Product: Amul Milk 1L | Product remains in cart after re-login
TC_ADDRESS_005 | Verify User Can Add a New Delivery Address | User is logged in | Validate address addition | Go to Profile or Checkout page Click “Add Address” Fill in address details (Name, Phone, Pincode, Street, Landmark) Select address type (Home/Office) Click “Save” | Name: Aishwarya, Phone: 9876543210, Pincode: 600119, Street: OMR Road, Type: Home | Address is saved and listed under delivery options